2010 PHILANTHROPY DAY

TIMELINE

(Update 8.12.10)

02/23/10

UPD2009 2nd Oversight Committee Meeting  

04/15/10

1st Steering Committee Meeting (3:30 – 5 pm UW of SL) 

05/13/10

2nd Steering Committee Meeting (4- 5 pm UW of SL)
05/15/10

Send Call for Nominations to USFR and 




UNA  (card ).  Have website ready (e-mail)

05/25/10

John & Carol Firmage accepted Honorary Chair Position
05/28/10

Selection Committee Invitations Sent and committee 




webspace available
06/10/10
3rd  Steering Committee Meeting (4- 5 pm UW of SL)
06/11/10

Call for Nominations Deadline 

Pull awards website information.

06/15/10

Selection Committee Packets Assembled

06/23/10

Selection Materials Distributed

06/26/10

Sponsorship Brochure ready.

07/01/10

Save the Date Email #1
07/07/10

Selection Committee meets (Alta Club)

07/08/10
4th Steering Committee Meeting (4- 5 pm UW of SL)
07/15/10

Save the Date Email #2

07/30/10

UPD2010 1st Oversight Committee Mtg. by this date
08/12/10

5th Steering Committee Meeting. (4- 5 pm UW of SL)
08/18/10

Honorees announced, Sponsorship letters drop, 




Registration Open, 
08/25/10

Video Production in process

09/01/10

Website Ready to go

09/09/10

Publicity regarding UPD and Scholarships goes out.

09/09/10

6th Steering Committee Meeting. (4- 5 pm UW of SL)
09/17/10
All sponsorships (names) must be received and given to Stephanie, John & Jen.

09/23/10
Final proof of invitation 

09/25/10

Second letter to Honorees which includes instructions

and request to send table names). 

09/25/10

Heart & Hands email blast to UNA and USFR

Wk of 09/27/10
Video filming takes place.

09/28/10

Sponsor Thank You Letters mailed.

10/05/10 
Invitations sent by mail and email.

10/07/10

7th  Steering Committee Meeting (4- 5 pm UW of SL)

10/08/10
Sponsorships closed to leave room for individual registrations.  Individual registrations limited to 5 guests each.

10/14/10
Invitations mailed and e-mail reminder that (no Heart & Hands nominee information will be accepted after 10/27/10.) Get Honorary Chair(s) to sign H&H Certificates.

10/15/10

Video Taping Completed.

10/27/10
Deadline for receipt of RSVP’s, including Heart &

Hands and Sponsorship information.

10/27/10
Deadline for receipt of program information, and sponsorship information including logos

11/05/10
Programs go to print 
11/09/10
On-line registration closed 

11/09/10
Video Editing Complete 

11/11/10
8th (final) Steering Committee Meeting (4- 5 pm UW of SL)
11/13/10
Table assignment meeting 

(Kathleen, Rebecca, Jennifer, Carol).
11/16/10

Final Steering Committee luncheon meeting.




(Little America)
11/18/10
Philanthropy Day Luncheon at Little America.  (Committee arrive at 9:00 a.m. and stay until cleanup complete.)
TBD
2010 UPD Wrap-up Meeting 

\\PCV-DFS1\DATA\FOUNDATION\USERS\PCCWOODS\WPDOCS\Philanthropy Day 2010\TIMELINES\2010 TIMELINE for inclusion on website 8.12.10.doc

