
2010 Philanthropy Day

Steering Committee Meeting #2 Notes

5.13.10

Attendance:  Ginette Bott, Rebecca Dutson (conducting), Kathleen Gardner, Jennifer Schreiter, Kai Wilson, Carol Woodside.  Excused:  Chris Arthur, Therese Clay, Stephanie Harpst. Debbie Mintowt, Anne O’Brien, Robin Pratt, Roland Radack, Gwen Springmeyer.

Welcome & Introductions:  Introductions were made.  Ginette Bott, Chief Marketing Officer with Utah Food Bank was welcomed.  Ginette will be working with Robin Pratt and Gwen Springmeyer in recruiting volunteers for the Utah Philanthropy Day event.

Potential additional members.  Debbie Mintowt is working to recruit David Goldsmith (Social Networking) to help with Publicity and Stephanie is recruiting John Pingree (Intermountain Healthcare) to help with Sponsorships.

Job Descriptions:   Revised 2010 Job Descriptions have been received from Therese Clay (Video Design), Kathleen Gardner (Logistics), Debbie Mintowt (Publicity and UPD Liaison with USFR), Robin Pratt (Volunteers), and Kai Wilson (Finance).  Revision is underway on Heart & Hands, Records Retention (Carol Woodside), Awards (Chris Arthur and Roland Radack), Sponsorships (Stephanie Harpst) and Administrative Assistant (Jennifer Schreiter).  Some activities previously handled by various committee members will be shifting to the Administrative Coordinator position. 

Honorary Chairs:  John and Carol Firmage have been invited to serve as Honorary Chairs.  Rebecca is waiting to hear back from them.  The question was raised if there could be a problem with nominating last year’s recipients to sit as honorary chairs the following year.  The consensus was there is no problem.

2010 Budget:  A proposed 2010 Budget, to be presented to the Oversight Committee and Honorary Chairs, was distributed and discussed.  Sponsorships have been set at $30,000.  The cost of the meals will be as quoted in the contract.  Two signatures are required on all checks.  Check signing authority – Chris Arthur, Anne O’Brien, Rebecca Dutson.  After conducting an inventory, it was reported we have 191 H&H pins and 300 H&H Certificates on hand.  We will not have to order either pins or certificates this year.  We are anticipating some softness in registrations in 2010.

Awards Selection:  Chris Arthur and Roland Radack will oversee the awards selection process.  Participants on the Selection Committee are being recruited.  In 2010, one award category (Next Generation Spirit of Giving) has been eliminated.  Nominations will be invited 5/14/10, with a submission deadline of 6/12/10.

Publications:  The postcard was sent to the printer last week with revised mailing lists.  Postcard should be received in the next few days.

Publicity:  Put Debbie Mintowt (Publicity) as an agenda item at the next meeting.

Logistics:  The November 18, 2010 date is firm on the Little America calendar.  Little America will not “boot” the UPD Event, and “booting” is the only way we would be moved to Grand America at the same rates.  The consensus of the group was we are happy at Little America even if it means limiting attendance to 800.  The contract is still pending, as we are trying to retain last year’s meal price, and eliminate the deposit.

Video:  Digital Bytes is “on board” again with video production.  Filming will take place in the Salt Lake United Way offices again, and filming dates will be set after honorees are chosen.

Timeline:  Notes from the 4/15/10 meeting and timeline were reviewed and changes noted.

Registration/Website:  Jen Schreiter is updating the website.  She is working on a password-protected page for private information, and uploading the updated nomination forms.  Jen has the UPD Letterhead Template.  If anyone needs it, just let her know.

Volunteers:  Robin will set a meeting date for the Volunteer Recruitment Chairs (Ginette Bott, Gwen Springmeyer, Robin Pratt) to coordinate information.

Next Meeting.:  6/10/10, 4:00 pm in the United Way Offices, 175 South West Temple Street, Garden Level Suite 30.

5/13/10 UPD Steering Committee Meeting

ACTION ITEMS

Rebecca Dutson
Follow-up with John and Carol Firmage, regarding Honorary Chair acceptance.

Begin discussions on continuing/replacing 3rd Sun webpage sponsorship.

Work with Chris and Roland on awards selection process.

Work with Jen and Carol in getting meeting notes, timeline, etc. in secure website “Committee Space.”

Put Debbie Mintowt (Publicity) in prominent place on next meeting agenda.

Stephanie Harpst 

Work with Rebecca on securing Sponsorship replacement.

Jennifer Schreiter

Continue getting website updated.

Work with Rebecca and Carol in getting meeting notes, timeline, etc. in secure website “Committee Space.”

Robin Pratt

Meet with Gwen Springmeyer and Ginette Bott to coordinate volunteer recruitment activities.

Carol Woodside

Prepare meeting notes.

Update Timeline.

Send Volunteer information to Ginette.

Send Job Description to Kathleen.

Work with Rebecca and Jen in getting meeting notes, timeline, etc. in secure website “Committee Space.” 

All

Update personal job description.


